## Tabelle2
Munich |  |  |  | Berkeley
Day 1 | 8:00 | 8:00 | Kick off |  | 23:00
| 9:00 | 9:00 | Working phase | Day 1 | 0:00
| 10:00 |  |  |  | 1:00
| 11:00 |  |  |  | 2:00
| 12:00 | 12:00 | Group Status Meeting |  | 3:00
| 13:00 |  | Functional Teams |  | 4:00
| 14:00 |  | Functional Teams |  | 5:00
| 15:00 |  |  |  | 6:00
| 16:00 |  | Presentations and groups |  | 7:00
| 17:00 | 17:00 | Lunch |  | 8:00
| 18:00 | 18:00 | Dinner |  | 9:00
| 19:00 | 19:00 | Milestone presentation to Berkeley - Video conferencing |  | 10:00 | 10:00 | Take over from Munich
| 20:00 |  |  |  | 11:00
| 21:00 | 21:00 | Definition of working packages for next day |  | 12:00
| 22:00 | 22:00 | End of Day 1 |  | 13:00
| 23:00 |  |  |  | 14:00
Day 2 | 24:00 |  |  |  | 15:00
| 25:00 |  |  |  | 16:00
| 26:00 |  |  |  | 17:00
| 27:00 |  |  |  | 18:00 | 18:00 | Group Meeting/ integration/ overall coordination.
| 28:00 |  |  |  | 19:00
| 29:00 |  |  |  | 20:00
| 30:00 |  |  |  | 21:00
| 31:00 | 31:00 | Take over from Berkeley* |  | 22:00 | 22:00 | Take over to Munich*
| 32:00 | 32:00 | Kick off |  | 23:00 |  | * Passing issues from Berkeley to Munich will take place mainly written. However, at least one person on each side should be available in the morning (7 am Germany /evening (10 pm Berkeley) respectively to comment orally
| 33:00 | 33:00 | Working phase | Day 2 | 0:00
| 34:00 |  |  |  | 1:00
| 35:00 |  |  |  | 2:00
| 36:00 | 36:00 | Group Meeting |  | 3:00
| 37:00 |  |  |  | 4:00
| 38:00 |  |  |  | 5:00
| 39:00 |  |  |  | 6:00
| 40:00 |  |  |  | 7:00
| 41:00 | 41:00 | Lunch |  | 8:00
| 42:00 | 42:00 | Integration phase |  | 9:00
| 43:00 | 43:00 | Milestone presentation to Berkeley - Video conferencing |  | 10:00 | 10:00 | Take over from Munich
| 44:00 |  |  |  | 11:00
| 45:00 | 45:00 | Definition of working packages for next day |  | 12:00
| 46:00 | 22:00 | End of Day |  | 13:00
| 47:00 |  |  |  | 14:00
Day 3 | 48:00 |  |  |  | 15:00
| 49:00 |  |  |  | 16:00
| 50:00 |  |  |  | 17:00
| 51:00 |  |  |  | 18:00 | 18:00 | Group Meeting/ integration/ overall coordination.
| 52:00 |  |  |  | 19:00
| 53:00 |  |  |  | 20:00
| 54:00 |  |  |  | 21:00
| 55:00 | 55:00 | Take over from Berkeley* |  | 22:00 | 22:00 | Take over to Munich*
| 56:00 | 56:00 | Kick off |  | 23:00
| 57:00 | 57:00 | Working phase | Day 3 | 24:00
| 58:00 |  |  |  | 25:00
| 59:00 |  |  |  | 26:00
| 60:00 | 60:00 | Group Meeting |  | 27:00
| 61:00 |  |  |  | 28:00
| 62:00 |  |  |  | 29:00
| 63:00 |  |  |  | 30:00
| 64:00 |  |  |  | 31:00
| 65:00 | 65:00 | Lunch |  | 32:00
| 66:00 | 66:00 | Integration phase |  | 33:00
| 67:00 | 67:00 | Milestone presentation to Berkeley - Video conferencing |  | 34:00 | 34:00 | Take over from Munich
| 68:00 |  |  |  | 35:00
| 69:00 | 69:00 | Definition of working packages for next day |  | 36:00
| 70:00 | 22:00 | End of Day |  | 37:00
| 71:00 |  |  |  | 38:00
Day 4 | 72:00 |  |  |  | 39:00
| 73:00 |  |  |  | 40:00
| 74:00 |  |  |  | 41:00
| 75:00 |  |  |  | 42:00 | 42:00 | Group Meeting/ integration/ overall coordination.
| 76:00 |  |  |  | 43:00
| 77:00 |  |  |  | 44:00
| 78:00 |  |  |  | 45:00
| 79:00 | 79:00 | Take over from Berkeley* |  | 46:00 | 22:00 | Take over to Munich*
| 80:00 | 80:00 | Kick off |  | 47:00
| 81:00 | 81:00 | Working phase | Day 4 | 48:00
| 82:00 |  |  |  | 49:00
| 83:00 |  |  |  | 50:00
| 84:00 | 84:00 | Group Meeting |  | 51:00
| 85:00 |  |  |  | 52:00
| 86:00 |  |  |  | 53:00
| 87:00 |  |  |  | 54:00
| 88:00 |  |  |  | 55:00
| 89:00 | 89:00 | Lunch |  | 56:00
| 90:00 | 90:00 | Integration phase |  | 57:00
| 91:00 | 91:00 | Milestone presentation to Berkeley - Video conferencing |  | 58:00 | 58:00 | Take over from Munich
| 92:00 |  |  |  | 59:00
| 93:00 | 93:00 |  |  | 60:00
| 94:00 | 22:00 | End of Day |  | 61:00
| 95:00 |  |  |  | 62:00
| 96:00 |  |  |  | 63:00
| 97:00 |  |  |  | 64:00
| 98:00 |  |  |  | 65:00
| 99:00 |  |  |  | 66:00 | 66:00 | Group Meeting/ integration/ overall coordination.
| 100:00 |  |  |  | 67:00
| 101:00 |  |  |  | 68:00
| 102:00 |  |  |  | 69:00
| 103:00 |  |  |  | 70:00 | 70:00 | Finalization
Fine tuning, finalization and further coordination on ad-hoc basis the following day.

## Tabelle1
Day 1 (Thursday):
Munich |  | Berkeley
8:30 | Kick off | 23:30 | XX
9:00 | Working phase | 0:00 | XX
12:00 | Group Meeting | 3:00 | XX
17:00 | Lunch | 8:00 | XX
18:00 | Integration phase | 9:30 | Kick-off
19:00 | Milestone presentation to Berkeley - Video conferencing | 10:00 | Take over from Munich
21:00 | Definition of working packages for next day | 12:00
22:00 | End of Day | 13:00
3:00 | XXX | 18:00 | Group Meeting/ integration/ overall coordination.
4:00 | XXX | 19:00 | Documentation and preparation to pass over to Germany (via email, CVS etc.)
Day 2 (Friday):
Munich |  | Berkeley
7:00 | Take over from Berkeley
8:30 | Kick off | 23:30 | XX
9:00 | Working phase | 0:00 | XX
12:00 | Group Meeting | 3:00 | XX
17:00 | Lunch | 8:00 | XX
18:00 | Integration phase | 9:00 | Kick-off
19:00 | Milestone presentation to Berkeley - Video conferencing | 10:00 | Take over from Munich
21:00 | Definition of working packages for next day | 12:00
22:00 | End of Day | 13:00
3:00 | XXX | 18:00 | Group Meeting/ integration/ overall coordination.
4:00 | XXX | 19:00 | Documentation and preparation to pass over to Germany (via email, CVS etc.)
Day 3 (Saturday):
Munich |  | Berkeley
7:00 | Take over from Berkeley | 22:00 | At least 1 person available to (orally) pass over work of the day to Munich
8:30 | Kick off | 23:30 | XX
9:00 | Working phase | 0:00 | XX
12:00 | Group Meeting | 3:00 | XX
17:00 | Lunch | 8:00 | XX
18:00 | Integration phase | 9:00 | Kick-off
19:00 | Milestone presentation to Berkeley - Video conferencing | 10:00 | Take over from Munich
21:00 | Definition of working packages for next day | 12:00
22:00 | End of Day | 13:00
3:00 | XXX | 18:00 | Group Meeting/ Integration/ overall coordination.
4:00 | XXX | 19:00 | Documentation and preparation to pass over to Germany (via email, CVS etc.)
Day 4 (Sunday):
Munich |  | Berkeley
7:00 | Take over from Berkeley | 22:00 | At least 1 person available to (orally) pass over work of the day to Munich
8:30 | Kick off | 23:30 | XX
9:00 | Working phase | 0:00 | XX
12:00 | Group Meeting | 3:00 | XX
17:00 | Lunch | 8:00 | XX
18:00 | Integration phase | 9:00 | Kick-off
19:00 | Milestone presentation to Berkeley - Video conferencing | 10:00 | Take over from Munich
21:00 |  | 12:00
22:00 | End of Day | 13:00
3:00 | XXX | 18:00 | Group Meeting/ overall coordination.
4:00 | XXX | 19:00 | Documentation and preparation to pass over to Germany (via email, CVS etc.)
Following Days:
Fine-Tuning coordination